## Tasktime-sheet
CONFIDENTIAL: TO GROUP MEMBERS ONLY
Work
Phase 1: Planning & Setup (Week 1–2)
Tasks
Finalize SRS - Software Requirement gathering
Decide tech stack (Next.js, Node.js/Express, PostgreSQL, React Native/Flutter).
Set up repo structure (frontend, backend, mobile, shared components).
Configure development environment (CI/CD pipeline, GitHub/GitLab, linting, formatting).
Deliverables
Project skeleton (monorepo or separate repos).
Basic CI/CD setup (dev + staging).
Phase 2: Backend Core Development (Week 3–6)
Tasks
Implement authentication (JWT/OAuth, role-based access).
Build core APIs: Users, Bookings, Estimates, Payments (dummy first).
Design database schema & ER diagrams.
Integrate Maps API (Google/Mapbox) for distance calculations.
Deliverables | Running backend with Swagger/OpenAPI docs.
Unit tests for major APIs.
Phase 3: Website (Customer-Facing) (Week 5–9)
Tasks
Build public landing page (services, about, contact).
Implement booking wizard (Step-by-step: Service → Address → Items → Estimate → Payment).
Add user login/register.
Show booking history & tracking page.
Deliverables
Responsive Next.js website (MVP booking flow working).
Connected to backend APIs.
Phase 4: Admin Dashboard (Week 5–9, parallel with Phase 3)
Tasks
Implement login & role-based access.
Booking management UI (search, filter, assign drivers).
Fleet & staff management module.
Reports (basic bookings/revenue table).
Deliverables
Admin panel with at least 3 core modules: Bookings, Users, Drivers.
Phase 5: Driver Mobile App (Week 7–11)
Tasks
Build login & job list.
Accept/reject booking flow.
Track job status (Arrived → Pickup → En Route → Delivered).
Upload images + get digital signature.
Deliverables
Mobile app (React Native/Flutter) connected to backend APIs.
Notifications enabled (via Firebase/OneSignal).
Phase 6: Payments & Notifications (Week 10–13)
Tasks
Integrate payment gateway (Razorpay/Stripe).
Invoice generation (PDF + email).
SMS/email/push notifications (booking confirmed, driver assigned, delivered).
Deliverables
End-to-end working payment + notification flow.
Phase 7: Testing & QA (Week 11–13)
Tasks
Unit, integration, and end-to-end testing.
Load testing for backend APIs.
Security testing (auth, data isolation).
Deliverables
Test reports.
Bug fixes before launch.
Phase 8: Deployment & Launch (Week 14)
Tasks
Deploy backend (AWS/DigitalOcean/Render).
Deploy website (Vercel/Netlify).
Mobile app (Play Store / App Store submission if needed).
Deliverables
Production-ready SaaS platform (MVP release).
Milestone 1 (Week 2): Repo setup + backend skeleton ready.
Milestone 2 (Week 6): Core APIs + DB working with test data.
Milestone 3 (Week 9): Website booking flow & admin dashboard MVP live on staging.
Milestone 4 (Week 11): Driver app MVP working with real-time status.
Milestone 5 (Week 13): Payments + notifications fully integrated.
Milestone 6 (Week 14): MVP launch (end-to-end working platform).
extra features (multi-language, AI pricing, franchise system, etc.).

## DB-Tables
CONFIDENTIAL: TO GROUP MEMBERS ONLY
user
cid_ pk not null

## uml
Use case diagram FEATURES
A use case diagram mainly shows the actors and what they do (their interactions with the system).
It focuses on who (actors) performs which actions (use cases) inside the system boundary — not how those actions work internally.
1 | customer/ driver/ admin/ employee | user in page + validations
signup
update details page
profile page after signin + space to upload other details - like address/mobile/cause.. Etc
2 | customer | Register an account
Login / Logout
View & Update Profile
View available service types (Local, Interstate, Office Shifting, etc.)
Get quotation (based on goods and distance)
Book service (choose pickup, drop address, service type, vehicle type)
Upload documents (ID proof, goods list)
Make payment (Cash/Card/UPI)
Track shipment in real-time
View booking history and receipts
Cancel booking (if not yet picked up)
Provide feedback or complaint
| Driver | Login
View assigned bookings
Update booking status (Picked up / In Transit / Delivered)
Update live location (tracking)
Upload delivery proof (photo, signature)
| Employee | Login
View all bookings
Assign driver and vehicle
Update service or payment details
Communicate with customer
Generate invoices
| Manager | Approve or reject bookings
Verify uploaded documents
Manage branches and employees
Handle complaints
Generate reports (daily bookings, payments, service stats)
| Admin | Manage all users (CRUD)
Manage roles (Customer, Employee, Manager, Driver)
Manage system configuration
View and export reports
Monitor audit logs and system activities
System Modules
1. User Management (Person, Role, PersonRole)
2. Booking Management (Booking, Goods)
3. Payment Management
4. Tracking Module (LocationHistory)
5. Vehicle Management
6. Branch & Address Module
7. Document Management
8. Audit Log Module
9. Service Type Module
who does what
Customer → Register → Login → View Service Types → Book Service
→ Add Pickup & Drop Address → Upload Goods List → Make Payment
→ Booking Confirmed → Receive Notification → Track Shipment
Manager → Login → View Pending Bookings → Verify Documents
→ Assign Employee & Driver → Approve Booking
Driver → Login → View Assigned Bookings → Update Status (Picked/Delivered)
→ Update Location → Upload Delivery Proof

## frontend
homepage/landing | header | locations - inner navbar, blogs, see professional movers, get quote button
banner
| chatbot | employee will talk - telephone link will be provided / artificial intell will talk or chat / presaved doc JS
google map tracking
invoice form generation
| price calculation (distance based) | front or backend?
caution/damage case handling
| halfway cancellation policy | listing other policy guidelines too - maybe separate page for terms and policies
| parcel weight measurement | how will It be done? Manually entered by the user: company person will come
blogs
social media links
get a quote
faqs section
footer for quick links
| email js form | fill trip details and submit
calculate moving cost popup - sticked/closeable
whatsapp call/chat button - sticked
call button sticked
about us
famous city buttons with moving charges and other info
services section on homepage
testimonials
important tips / blogs section marketting type section
left pane opening and closing hour information
| services page | separate with all services in sidebar(active clickable)
Home Relocation
Office Relocation
Car Transportation
Insurance Management
Warehousing and Storage
Local Shifting
Domestic Moving
admin panel functions
| who will assign the driver? | employee manually

## activities
activities |  | done by
1 | asked max packers and movers for quotation | vaibhavi | Hello! I need a quotation for shifting my household items.
2 | "" "" "" urban clap

## Interview
Questions
1 | Why did you choose this project?
2
3
4
5
6
7
8
9
10